Aims, Objectives, and SMART Goals

Project Aim

To systematically investigate how lesion-aware adversarial perturbations affect the decision-making and adversial robustness of medical imaging foundation models.

Project Objectives

- Review papers on adversarial robustness and medical imaging foundation models.

To complete a structured paper review by Week 8, producing a 1,000–1,200-word summary and a table of ≥15 key papers. Success is defined as understanding ≥90% domain terminology and identifying findings that guide model and attack selection.

- Reproduce key adversarial attack algorithms for use in experiments.

To reproduce two representative attacks (PGD and CW/DeepFool) by Week 10, confirmed by generating adversarial examples for ≥500 test images with behavior consistent with published results.

- Select suitable datasets and foundation models for evaluation.

To select one dataset (NIH or CheXpert) and 1–2 foundation models by Week 11, with working preprocessing and inference pipelines. Completion is evidenced by a short justification note.

- Integrate model and attack code into a unified experimental framework.

To unify preprocessing, inference, and attack calls into a common API by Week 13, with standardized inputs/outputs and verified compatibility across chosen models and attacks.

- Implement lesion-aware adversarial attacks using hotspot-based masks.

To generate binarized attention- masks from the selected foundation models (e.g., Grad-CAM or attention heatmaps), apply constrained perturbations within these regions and evaluate the effect to the FM by Week 16. The task is considered complete when preprocessing, masked-attack generation, post-processing, and evaluation have been successfully carried out on the test set.

- Compare lesion-aware and non-lesion attacks across selected models.

To apply perturbations to unmasked images by full preprocessing, attack generation, post-processing, and robustness evaluation by Week 1 of next semester. Completion is defined by obtaining comparable metrics to the lesion-aware setting and producing the required analysis across selected models and ε values.

- Prepare the final dissertation and presentation.

To produce a full dissertation draft (≥5,000 words) including introduction, methodology, results, and discussion, and complete a 10-minute presentation by Week 4 of next semester. Success is defined by incorporating supervisor feedback into the final revision.

Summary of Work Completed

As of Week 14, the project has successfully completed the first three SMART objectives and the foundational elements of the fourth. The work accomplished demonstrates a strong theoretical grounding and has established a robust technical baseline, ready for the critical experimental phase (Objective 5: Lesion-Aware Attack Implementation).

2.1 Literature Review and Project Definition

The Literature Review (Objective 1) was completed by Week 8, yielding a structured summary and a catalog of over 18 key papers. The review was highly critical, a key requirement for an excellent report—and directly shaped the project's direction:

- Theoretical Foundations: The review confirmed that Iterative Gradient Attacks (PGD) (Carlini & Wagner, 2017) and Minimum-Distortion Attacks (C&W) represent the gold standard for testing adversarial robustness. These were selected as the core "stress tests" for the project. (If there is extra time, FSGM and deepfool will also be used for evaluation.)

- Identification of Academic Gap: A critical analysis revealed that existing adversarial attacks in medical imaging primarily target CNN architectures and rely on global perturbations (Lp constraints) (Finlayson et al., 2019). This approach fundamentally overlooks the lesion-centricity of clinical diagnosis.

- Strategic Refinement: This insight led to the project's strategic refinement to focus exclusively on Chest X-Ray Foundation Models (FMs) and to pursue the novel approach of Lesion-Aware Adversarial Perturbations (Li et al., 2025). The methodology was set to use model interpretability methods (Grad-CAM/Attention) as proxies to define a spatial mask, ensuring high academic impact and innovation.

2.2 Methodology and Component Validation

The project follows a modular methodology, establishing independent Data, Model, and Attack layers to ensure experimental control and reproducibility.

- Attack Algorithm Functional Validation (Completed Objective 2): The core algorithms—PGD, C&W, and DeepFool—have been successfully reproduced and functionally validated on generic benchmark datasets (e.g., CIFAR). The validation results confirmed algorithm integrity, notably achieving a 100% success rate for C&W targeted attacks with minimal L2 distortion.

- Model and Data Readiness (Completed Objective 3): The CheXpert dataset was selected for its scale and multi-label complexity (Irvin et al., 2019). The CheXzero Foundation Model (Tiu et al., 2022), a complex Transformer-based architecture, has been successfully pulled locally, and its Model Wrapper has been integrated to provide a unified inference pipeline.

- Framework Integration Status (Completed Objective 4 - Partial): The Data Module and the Model Wrapper are complete. The attack algorithms have been validated but have not yet been standardized and integrated into the final unified API framework. This standardization is the critical remaining step for Objective 4.

2.3 Results & Experiment diagram design

| Milestone | Planned Completion | Status | Key Achievement |
| --- | --- | --- | --- |
| Literature Review (Obj. 1) | Week 8 | Completed | Defined the Lesion-Aware focus. |
| Attack Function Validation (Obj. 2) | Week 10 | Completed | Confirmed PGD, C&W, DeepFool code integrity. |
| FM Model Integration (Obj. 3 & 4-Part) | Week 11 | Completed | CheXzero pulled, Model Wrapper established. |
| Unified API Framework (Attack Integration) | Week 13 | In Progress | Current focus: Standardizing attack interfaces. |

2.4 Critical Analysis and Project Adaptation

Current Challenge: Environment and API Integration Consistency

Problem Dissection: Different papers rely on incompatible codebases and library versions, causing frequent dependency conflicts when reproducing PGD, C&W, and DeepFool. These inconsistencies affect imports, tensor behaviors, and model loading, making a unified execution environment impractical.

Adaptation Strategy: I assigned each experiment its own Anaconda environment and reorganized the project into three modules—Data, Model, and Attack—to isolate dependencies, standardize interfaces, and ensure stable integration for later lesion-aware attack experiments. Overall, my research plan is progressing smoothly and no changes are necessary.

Plan for the Remainder of the Project, including Personal Reflection and Self-Assessment

The project is currently on track to meet its foundational milestones, with Objectives 1-3 (Literature Review, Attack Reproduction, Model/Dataset Selection) successfully completed. The remaining major tasks (Objectives 4-7) involve the experimental core and final report writing. To control computational complexity and ensure timely completion, I have strategically modified the experimental scope. PGD (Projected Gradient Descent) and C&W (Carlini & Wagner) attacks will be the core, mandatory methods for in-depth analysis. FGSM (Fast Gradient Sign Method) and DeepFool are reserved as secondary/contingency options. Model selection is restricted to a single CheXzero Foundation Model, and perturbation levels (ε) will be limited to three representative values to streamline the comparative analysis (Objective 6). This focused approach strengthens the viability of the completion plan.

Risks and Mitigations

| Potential Future Risk | Mitigation Strategy |
| --- | --- |
| Lesion Mask Quality Failure (Core Risk): Generating a high-fidelity, clinically relevant lesion mask (M) from the Transformer FM (e.g., via Grad-CAM) proves unfeasible or unreliable. | Contingency Research Pivot: If mask quality is poor, I will abandon the lesion-aware perturbation experiments (δ’= δ⊙M ). I will pivot the research focus to a deep, comparative evaluation of the four attack methods (PGD, C&W, FGSM, DeepFool) on the base model, ensuring the project aligns with the core thesis objective of "Evaluating Adversarial Robustness." |
| API Encapsulation Failure: Discovering that third-party GitHub code for attacks or models is incomplete or mismatched with published papers during the API integration (Objective 4). | Redundancy and Validation: I will perform a comprehensive code validation step before final integration. If external code is unusable, I will immediately switch to validated implementations from robust adversarial libraries (e.g., TorchAttack/Advertorch) or rely on my successfully reproduced PGD/C&W custom implementations to ensure the API is delivered on time. |

The project has been an invaluable learning experience. I have significantly developed my Project Management skills, recognizing the necessity and benefits of establishing a detailed long-term plan and rigorously adhering to it. My Problem-Solving ability improved by learning to quickly synthesize keywords into targeted searches for relevant academic papers to overcome complex technical hurdles. If I were to start the project again, I would dedicate more time to early research on lesion mask generation techniques, avoiding the current situation where a core technical dependency (mask quality) remains untested. Furthermore, I would synchronize the code reproduction and validation work with the initial paper reading phase to pre-emptively confirm the usability and completeness of external code repositories.

I believe my progress currently warrants a conditional grade estimate. First-Class (A Grade) is achievable if the Lesion Mask Generation is successful and the Attack API is fully functional. This outcome would meet all criteria, including the core innovative element, demonstrating exceptional sophistication and critical analysis.Upper Second (B Grade) will be projected if the Lesion Mask fails and a research pivot is required. While my Work Completed (Literature Review, basic attack reproduction) is strong, the necessary shift would indicate a shortfall in Critical Analysis and Professionalism & Process criteria regarding foresight and the execution of the original, innovative scope.

References

- Carlini, N. & Wagner, D., 2017. Towards evaluating the robustness of neural networks. Proceedings of the 2017 IEEE Symposium on Security and Privacy (SP), pp.39–57. doi:10.1109/SP.2017.49. IEEE Computer Society+1

- Finlayson, S.G., Chung, H.W., Kohane, I.S. & Beam, A.L., 2019. Adversarial attacks against medical deep learning systems. arXiv preprint arXiv:1804.05296. arXiv+1

- Li, L., Huang, Y., Li, C., Zhou, F., Li, J. & Ghazali, K.H., 2025. LatAtk: A medical image attack method focused on lesion areas with high transferability. Journal of Imaging, 11(11), 404. doi:10.3390/jimaging11110404. MDPI+1

- Irvin, J., Rajpurkar, P., Ko, M., Yu, Y., Ciurea-Ilcus, S. et al., 2019. CheXpert: A large chest radiograph dataset with uncertainty labels and expert comparison. Proceedings of the AAAI Conference on Artificial Intelligence, 33(1), pp.590–597. doi:10.1609/aaai.v33i01.3301590. arXiv+2AAAI+2

- Tiu, E., Talius, E., Patel, P., Langlotz, C.P., Ng, A.Y. & Rajpurkar, P., 2022. Expert-level detection of pathologies from unannotated chest X-ray images via self-supervised learning. Nature Biomedical Engineering, 6(12), pp.1399–1406. doi:10.1038/s41551-022-00936-9.